## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Create a Course | Create an implement (Course) class | 1.5 |  | 2
| Create UI for Course creation | 2 |  | 2
View Course(s) | Create UI to View Course(s) | 2 | 0.5 | 2
View Course Details | Create UI to View Course Details (Grades, Subsections, etc) | 1 |  | 2
Input Grade(s) to Course | Implement adding Grade to a Course | 1 | 3 | 1
| Create UI for Grade inputing | 2 |  | 2
Create SubSections | Implement SubSections to allow adding grades to properly calculate Course Grade | 2 | 2 | 3
Change Grade(s) | implement updating existing Grade | 1
Delete Grade(s) | implement deleting existing Grade | 1
Allow (x) Grades to be dropped | implement 'X' Grades to be excluded towards Subsection | 1 | 1 | 1
Average all my Course | implement taking average of Assignents/SubSections | 0.25 |  | 1
Create Sample Rubrics | Create pre-built Rubrics like a Simple and Standard Rubric | 1.5
| Estimate Totals | 16.25 | 6.5 | 16 | 0 | 0
Simple Rubric is just one Subsection where everything is the same weight
Standard Rubric is with 2+ SubSections where each section has it's own weight and == 100%
Course has Name, Code, Professor. Will need List of Subsections and Subsections need a list of Grades.
Viewing Courses Need a List of Courses, and if a course is selected then it shows Current and End Grade.
SubSections has Name, Weight, and # of Assignments (Optional?)
Worked on 10/10 from 11AM to 3:30 and from 9PM to 2 AM